## Worksheet
Earned Value Worksheet
By: | B. Roseke
Project Name: |  | Build a House
Date: | 2021-10-11
Period Ending: |  | 2021-10-09
[7 empty] | Inputs |  |  | Current Status |  |  |  | Forecast
[14 empty] | Future Performance = Planned Performance (Variances are one time) |  |  | Future Performance = Past Performance |  |  | Budget and Schedule performance both affect future performance
ID | Task Name |  | Start | End | BAC | % Comp. | PV | EV | AC | SV | SPI | CV | CPI | EAC1 | VAC1 | TCPI1 | EAC2 | VAC2 | TCPI2 | EAC3 | VAC3 | TCPI3
[5 empty] | Budget at Completion |  | Planned Value | Earned Value | Actual Cost | Schedule Variance | Schedule Perf. Index | Cost Variance | Cost Perf. Index | Estimate at Completion | Variance at Completion | To-Complete Perf. Index | Estimate at Completion | Variance at Completion | To-Complete Perf. Index | Estimate at Completion | Variance at Completion | To-Complete Perf. Index
10 | Build Foundation |  | 2021-09-01 | 2021-09-22 | 45000 | 100% | 45000 | 45000 | 47000 | 0 | 1 | -2000 | 0.95745 | 47000 | -2000 | 0 | 47000 | -2000 | 0 | 47000 | -2000 | 0
20 | Framing |  | 2021-09-22 | 2021-10-08 | 35000 | 100% | 35000 | 35000 | 34500 | 0 | 1 | 500 | 1.0145 | 34500 | 500 | 0 | 34500 | 500 | 0 | 34500 | 500 | 0
30 | Exterior |  | 2021-10-04 | 2021-10-29 | 40000 | 35% | 8000 | 14000 | 12000 | 6000 | 1.75 | 2000 | 1.1667 | 38000 | 2000 | 0.92857 | 34285.7143 | 5714.2857 | 0.92857 | 24734.6939 | 15265.3061 | 0.92857
40 | Interior |  | 2021-10-11 | 2021-11-05 | 60000 | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 60000 | 0 | 1 | 60000 | 0 | 1 | 60000 | 0 | 1
50 | Finishing |  | 2021-11-08 | 2021-11-26 | 25000 | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 25000 | 0 | 1 | 25000 | 0 | 1 | 25000 | 0 | 1
|  |  |  | TOTAL | 205000 |  | 88000 | 94000 | 93500 | 6000 | 1.0682 | 500 | 1.0053 | 204500 | 500 | 0.99552 | 200785.7143 | 4214.2857 | 0.99552 | 191234.6939 | 13765.3061 | 0.99552
INSTRUCTIONS
1. Enter the first 5 columns only once, at the beginning of the project. This is the project schedule and budget baseline information, and it will only change when the project budget or schedule changes.
2. At the end of each period:
1. Enter the current date under 'Date'
2. Enter the Period Ending. This is the cutoff date for the project data used in the analysis (% complete, Actual Cost)
3. For each task, enter the percentage that is complete at the Period Ending date into the column "% complete"
4. For each task and enter the actual cost at the Period Ending date into the "Actual Cost (AC)" column.
3. Enter the applicable totals into the 'Earned Value Trend' report to view how the project has trended over time.
4. Enter the applicable totals into the 'Earned Value Report' for presentation to stakeholders.
INTERPRETATION OF RESULTS
Inputs
· PV (Planned Value) is the amount of work that should be done at the point of analysis, according to the schedule.
· EV (Earned Value) is the amount of work that is actually done.
· AC (Actual Cost) is the cost of the work that is currently complete
Current Status
· SV (Schedule Variance) is the amount that the project is ahead or behind schedule. Negative = Behind. Positive = Ahead.
· SPI (Schedule Performance Index) is the percentage behind or ahead of schedule. Below 1.0 = Behind. Above 1.0 = Ahead
· CV (Cost Variance) is the amount that the project is over or under budget. Negative = Over. Positive - Under
· CPI (Cost Performance Index) is the percentage over or under budget. Below 1.0 = Over Budget. Above 1.0 = Under Budget.
Forecast
· EAC (Estimate at Completion) is the final project cost that the project is trending towards.
· VAC (Variance at Completion) is the final cost variance (CV) that the project is trending towards.
· TCPI (To Complete Performance Index) is the CPI needed to finish the project on budget.
DEFINITIONS
PV | = Planned Value
= [(Date of Analysis - Start) / (End - Start)]
EV | = Earned Value
= [% Complete x BAC]
AC | = Actual Cost
= Estimated by the project manager
SV | = Schedule Variance
= [EV - PV]
SPI | = Schedule Performance Index
= [EV / PV]
CV | = Cost Variance
= [EV - AC]
CPI | = Cost Performance Index
= [EV / AC]
EAC1 | = Estimate at Completion, assuming future performance is according to plan, and past performance is not representative of future performance
= [AC + BAC - EV]
EAC2 | = Estimate at Completion, assuming future performance is similar to past performance
= [BAC / CPI]
EAC3 | = Estimate at Completion, assuming future performance is affected by both schedule and cost performance
= [AC + ((BAC - EV)/(CPI*SPI))]
ETC | = Estimate to Complete
= [AC + New ETC]
VAC | = Variance at Completion
= [BAC - EAC]
TCPI | = To-Complete Performance Index
= [ (BAC - EV) / (BAC - AC) ]

## Trend
Earned Value Trend Report
By: | B. Roseke
Date: | 2021-10-09
Period
Period Ending | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18 | 2021-09-25 | 2021-10-02 | 2021-10-09
PV | 0 | 6429 | 21429 | 36429 | 51563 | 66875 | 88000
EV | 0 | 6750 | 22500 | 41750 | 55500 | 69500 | 94000
AC | 0 | 7200 | 24000 | 44500 | 56000 | 71000 | 93500
SV | 0 | 321 | 1071 | 5321 | 3938 | 2625 | 6000
SPI | 1 | 1.05 | 1.05 | 1.15 | 1.08 | 1.04 | 1.07
CV | 0 | -450 | -1500 | -2750 | -500 | -1500 | 500
CPI | 1 | 0.94 | 0.94 | 0.94 | 0.99 | 0.98 | 1.01

## 2021-08-28
Earned Value Report
Project Name: | Build a House
By: | B. Roseke
Period Ending: | 2021-08-28
|  | Budget at Completion (BAC): | 205000
|  | Planned Value (PV): | 0
|  | Earned Value (EV): | 0
|  | Actual Cost (AC): | 0
|  | Schedule Variance (SV): | 0
|  | Schedule Performance Index (SPI): | 1
|  | Cost Variance (CV): | 0
|  | Cost Performance Index (CPI): | 1
Root Cause of Schedule Variance
N/A
Schedule Impact
N/A
Root Cause of Cost Variance
N/A
Budget Impact
N/A
Estimates at Completion
EAC 1: | 205000 | TCPI 1: | 1 | The existing budget trend will continue
EAC 2: | 205000 | TCPI 2: | 1 | The existing budget and schedule trend will continue
EAC 3: | 205000 | TCPI 3: | 1 | Selected EAC
Comments
The work is scheduled to start next week.

## 2021-09-04
Earned Value Report
Project Name: | Build a House
By: | B. Roseke
Period Ending: | 2021-09-04
|  | Budget at Completion (BAC): | 205000
|  | Planned Value (PV): | 6429
|  | Earned Value (EV): | 6750
|  | Actual Cost (AC): | 7200
|  | Schedule Variance (SV): | 321
|  | Schedule Performance Index (SPI): | 1.05
|  | Cost Variance (CV): | -450
|  | Cost Performance Index (CPI): | 0.94
Root Cause of Schedule Variance
The foundation was poured a day earlier than planned.
Schedule Impact
None
Root Cause of Cost Variance
The concrete was poured in cold weather and we needed to buy some heaters and tarps
Budget Impact
The cost of heaters was not budgeted for.
Estimates at Completion
EAC 1: | 205000 | TCPI 1: | 1 | The existing budget trend will continue | EAC's and TCPI's not correct in this week's report
EAC 2: | 205000 | TCPI 2: | 1 | The existing budget and schedule trend will continue
EAC 3: | 205000 | TCPI 3: | 1 | Selected EAC
Comments
The foundation was excavated and concrete poured.

## 2021-09-11
Earned Value Report
Project Name: | Build a House
By: | B. Roseke
Period Ending: | 2021-09-11
|  | Budget at Completion (BAC): | 205000
|  | Planned Value (PV): | 21429
|  | Earned Value (EV): | 22500
|  | Actual Cost (AC): | 24000
|  | Schedule Variance (SV): | 1071
|  | Schedule Performance Index (SPI): | 1.05
|  | Cost Variance (CV): | -1500
|  | Cost Performance Index (CPI): | 0.94
Root Cause of Schedule Variance
The project was able to capitalize on good weather to get slightly ahead of schedule.
Schedule Impact
Keep schedule as is for now.
Root Cause of Cost Variance
Costs continued to be higher than anticipated.
Budget Impact
Keep budget as is for now.
Estimates at Completion
EAC 1: | 205000 | TCPI 1: | 1 | The existing budget trend will continue
EAC 2: | 205000 | TCPI 2: | 1 | The existing budget and schedule trend will continue
EAC 3: | 205000 | TCPI 3: | 1 | Selected EAC | EAC's and TCPI's not correct in this week's report
Comments
Half of the foundation work is complete. The Contractor is working well and is competent. The project is trending over budget and the project team will look for savings in other areas.

## 2021-09-18
Earned Value Report
Project Name: | Build a House
By: | B. Roseke
Period Ending: | 2021-09-18
|  | Budget at Completion (BAC): | 205000
|  | Planned Value (PV): | 36429
|  | Earned Value (EV): | 41750
|  | Actual Cost (AC): | 44500
|  | Schedule Variance (SV): | 5321
|  | Schedule Performance Index (SPI): | 1.15
|  | Cost Variance (CV): | 2750
|  | Cost Performance Index (CPI): | 0.94
Root Cause of Schedule Variance
The framers were done their previous project and mobilized to the site early, before the foundation was done. They were able to do their setup work and start on the side of the building where the foundation was not started yet.
Schedule Impact
None
Root Cause of Cost Variance
Additional internal manpower was required to manage the early mobilization of the framing crew.
Budget Impact
Keep budget as is for now. TCPI of 2% suggests savings could still be found.
Estimates at Completion
EAC 1: | 207750 | TCPI 1: | 1.02 | The existing budget trend will continue
EAC 2: | 199412 | TCPI 2: | 1.02 | The existing budget and schedule trend will continue
EAC 3: | 199059 | TCPI 3: | 1.02 | Selected EAC
Comments
The framing crew mobilized early, which caused the schedule variance to go positive but the budget variance to go further negative. Notwithstanding previous negative budget variances, this lower CV should be partly recoverable.

## 2021-09-25
Earned Value Report
Project Name: | Build a House
By: | B. Roseke
Period Ending: | 2021-09-25
|  | Budget at Completion (BAC): | 205000
|  | Planned Value (PV): | 51563
|  | Earned Value (EV): | 55500
|  | Actual Cost (AC): | 56000
|  | Schedule Variance (SV): | 3938
|  | Schedule Performance Index (SPI): | 1.08
|  | Cost Variance (CV): | -500
|  | Cost Performance Index (CPI): | 0.99
Root Cause of Schedule Variance
The foundation is complete and the framing is proceeding on schedule
Schedule Impact
No changes
Root Cause of Cost Variance
We were able to recover some of the costs from previous periods due to diligent focus on finding savings, but the project is still slightly over budget.
Budget Impact
No changes
Estimates at Completion
EAC 1: | 20500 | TCPI 1: | 1 | The existing budget trend will continue
EAC 2: | 202000 | TCPI 2: | 1 | The existing budget and schedule trend will continue
EAC 3: | 194125 | TCPI 3: | 1 | Selected EAC
Comments
The foundation is complete and the Contractor has demobilized. The framing crew is on site and is expected to take another two weeks to finish their work.

## 2021-10-02
Earned Value Report
Project Name: | Build a House
By: | B. Roseke
Period Ending: | 2021-10-02
|  | Budget at Completion (BAC): | 205000
|  | Planned Value (PV): | 66875
|  | Earned Value (EV): | 69500
|  | Actual Cost (AC): | 71000
|  | Schedule Variance (SV): | 2625
|  | Schedule Performance Index (SPI): | 1.04
|  | Cost Variance (CV): | -1500
|  | Cost Performance Index (CPI): | 0.98
Root Cause of Schedule Variance
The framers continued their work and are on schedule.
Schedule Impact
No changes
Root Cause of Cost Variance
The framing Contractor invoiced aggressively for their work.
Budget Impact
No changes. The cash flow should recover after progress catches up with Contractor invoicing.
Estimates at Completion
EAC 1: | 206500 | TCPI 1: | 1.01 | The existing budget trend will continue
EAC 2: | 206286 | TCPI 2: | 1.01 | The existing budget and schedule trend will continue
EAC 3: | 205184 | TCPI 3: | 1.01 | Selected EAC
Comments
The framing is 70% done and the Contractor is on schedule to finish next week.

## 2021-10-09
Earned Value Report
Project Name: | Build a House
By: | B. Roseke
Period Ending: | 2021-10-09
|  | Budget at Completion (BAC): | 205000
|  | Planned Value (PV): | 88000
|  | Earned Value (EV): | 94000
|  | Actual Cost (AC): | 93500
|  | Schedule Variance (SV): | 6000
|  | Schedule Performance Index (SPI): | 1.0682
|  | Cost Variance (CV): | 500
|  | Cost Performance Index (CPI): | 1.0053
Root Cause of Schedule Variance
The project continues to be ahead of schedule due to aggressive scheduling of Contractors
Schedule Impact
No changes
Root Cause of Cost Variance
The savings generated by the project team due to early overruns, and the ahead-of-schedule nature of the project has put the Cost Variance into the black for the first time.
Budget Impact
No changes.
Estimates at Completion
EAC 1: | 204500 | TCPI 1: | 0.99552 | The existing budget trend will continue
EAC 2: | 200785.7143 | TCPI 2: | 0.99552 | The existing budget and schedule trend will continue
EAC 3: | 191234.6939 | TCPI 3: | 0.99552 | Selected EAC
Comments
The framing crew is complete and the de-mobilizing and the siding and roofing crews are on site. They are about 1/3 complete. The project is now under budget as well as ahead of schedule.